## Instructions
Pre-Award (Application) Instructions
All applicants are required to provide project/program milestones as part of their application. Instructions for completing each milestone attribute are provided below:
Milestone Name: Name or briefly describe the milestone and/or any deliverables.
Milestone Type: Choose an appropriate activity type from the choice list provided.
Status: Milestones should be assigned a "Not Started" status at the time of application.
Start Date: Enter the anticipated start date for the milestone.
Expected Date: Enter the expected date of completion for the milestone.
Percent Complete: Percent complete should be set to "0%."
Planned Amount: Enter the anticipated cost of completing the milestone.
Estimated Spent: This field should be left blank at the time of application.
Is Deliverable: Is a deliverable associated with the milestone?
Description: Provide a concise description of the milestone. If there are deliverables associated with the milestone, describe them here.
Progress Summary: This field should be left blank at the time of application.
Financial Reporting Instructions
As part of Financial Reporting, recipients are required to provide updated Status, Percent Complete, Estimated Spent, Start Date, Expected Date, and Progress Summary values for each milestone that was submitted at the time of application. If changes to other values are necessary, or if you need to add or delete milestones, those changes should be submitted separately as part of amendment or via a Grant Note.
Milestone Name: No changes
Milestone Type: No changes
Status: Update as necessary
Start Date: If the expected start date has changed, enter the new value. If work on the milestone has commenced, enter the actual value.
Expected Date: If the expected end date has changed, enter the new value. If work on the milestone has ended, enter the actual value.
Percent Complete: Update as necessary.
Planned Amount: No changes
Estimated Spent: Update as necessary with the estimated amount spent toward completing the milestone.
Is Deliverable: No changes
Description: No changes
Progress Summary: Enter a short summary describing progress made toward the milestone, if applicable.
Amendments and Changes
Updated milestones should be included as part of an amendment request when that amendment would change the values that were approved at the time of application. Changes to milestones may also be submitted via a Grant Note any time that a modification to the approved milestones are necessary. Submit the revised milestones will all appropriate attributes completed, per the instructions above. You may describe any changes using the Progress Summary field.
version 2.0 (2020-03-10)

## Milestones
| Submission Type |  |  | Date Prepared
# | Milestone Name | Milestone Type | Status | Start Date | Expected Completion Date | Percent Complete | Planned Amount ($) | Estimated Spent ($) | Is Deliverable | Description | Progress Summary
1 | [10 empty] | n/a for application
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
Note on B3: Name or briefly describe the activity to be carried out within the specified time frame and/or the deliverable to be produced. This activity and any deliverable(s) should be fully described and identifiable in the grant application. Please note that all activities to be carried out with the requested funding should be summarized in the Milestones section of the grant application. These may include activities such as “project oversight” that have not traditionally been considered “milestones.”
Note on C3: Choose the type of activity to be carried out from the choice list provided.
Note on D3: Please select a status from the drop down list in cell
Note on E3: Enter the date when it is anticipated that this activity or development of this deliverable will begin. This may be the start date for the project, or it may be later in the performance period
Note on F3: Enter the date when this activity or deliverable is expected to be completed.
Note on J3: Will this activity produce or result in an item that will be submitted to the Council as a deliverable (e.g., a plan, construction drawings, or a research report)? Select “Yes” or “No”.
Note on K3: Provide a concise description of milestones associated with each milestone type and any deliverables. Information provided should be detailed enough to provide the reader a clear understanding of the work to be conducted, including any subcontracting and deliverables; support the scope of work; and justify the budgeted costs. Describe what the deliverables are and description of them.
Note on L3: What is the current progress towards milestone completion? What has been completed so far?

## Choice Lists (hidden)
Milestones Types
Project Oversight and Grants Management
Planning
Environmental Compliance
Engineering and Design
Implementation: Non-Construction
Construction
Land Acquisition
Scientific Monitoring and Metrics
Data Management and Reporting
Long-Term Operations and Maintenance
Adaptive Management
Other
Is Deliverable?
Yes
No
Milestone Status
Not Started
In Progress
Complete
Submission Type
Application
Financial Report
Change or Amendment